## Team Formation
Team Formation and Project Idea
Team Name: | The A Team
Team Members: | Pruthvi Hammigi | Yashwanth Dharipelli | Anish Arumugam | Cooper Staples
Project Name : Selecting a location to build Tesla’s Gigafactory
Size : 4

## Vis-Obj
Date: | 2024-04-21 | Project #: | 01'
Project Manager:
Project Name: | Selecting a location to build Tesla’s Gigafactory
Vision | Tesla's Gigafactories are large-scale production facilities designed to produce electric vehicle batteries, energy storage systems, and solar products. These factories help Tesla to scale up production and reduce the cost of their products. The Gigafactories in Nevada and China have established a strong foundation, achieving significant return on investment and propelling electric vehicle adoption. To maintain this momentum, we envision building a new Gigafactory strategically located to optimize production efficiency and cost-effectiveness. This next-generation facility will leverage Tesla's existing expertise in large-scale manufacturing while incorporating cutting-edge research in logistics, transportation, and workforce development. Through rigorous site selection, we aim to achieve faster production ramp-up compared to previous facilities, reaching or exceeding established production targets within a shorter timeframe. This strategic expansion will solidify Tesla's leadership in electric vehicle production and accelerate the global transition to sustainable transportation.
Objective
To | Identify and recommend Tesla's Gigafactory location by Mar/31/2026, utilizing a budget of $141,551.
By | 2026-03-31
Within a cost of | 143390.5
Full Objective | Identify and recommend Tesla's Gigafactory location by Mar/31/2026, utilizing a budget of $141,551.

## ADKAR (hidden)
Organizational Change Management
|  | Current Status |  | Activities to implement change
How aware are people of the need to for the change this project will bring? | Awareness
What is the desire of people to support this change? | Desire
What knowledge do people have and need to make this change? | Knowledge
What is their ability to demonstrate new skills and behaviors? | Ability
What reinforcements do we need to apply to make the change stick? | Reinforcements

## Issues
Issues, Impediments, Problems, Assumptions & Risks Log
Project Details
Date: | 2024-04-21 | Project #: | 01'
Project Manager:
Project Name: | Selecting a location to build Tesla’s Gigafactory
| DESCRIPTION | DATE | ASSIGNED TO TASK # | STATUS
1 | Supply Chain and Logistics: Building a Gigafactory requires a robust supply chain to ensure a steady flow of raw materials, components, and equipment. Tesla would need to establish relationships with local suppliers and logistics partners to ensure efficient operations and minimize transportation costs. | 2024-04-21 | Camille- Supply Chain | Open
2 | Regulatory and Permitting Processes: Establishing a large-scale manufacturing facility like a Gigafactory requires navigating complex regulatory and permitting processes. Tesla would need to comply with local laws, environmental regulations, and obtain necessary permits, which can be time-consuming and involve bureaucratic hurdles | 2024-04-21 | Mary- Regulatory Affairs | Open
3 | Labor Laws and Workforce: Every country has unique labor market with specific labor laws and regulations. Tesla would need to navigate these laws, including regulations related to working hours, employee benefits, and labor unions. Adapting to the local workforce and ensuring a skilled labor pool for manufacturing operations could also pose challenges. | 2024-04-21 | Mary- Regulatory Affairs | Open
4 | Energy Infrastructure: Gigafactories require a significant amount of energy to operate. Tesla would need to assess the availability and reliability of the local energy infrastructure in the country to ensure uninterrupted power supply for its manufacturing operations. This may involve negotiating energy contracts and potentially investing in renewable energy sources. | 2024-04-21 | Doug - Engineering | Open
5 | Public Perception and Opposition: Large-scale industrial projects can sometimes face opposition from local communities or environmental groups concerned about the impact on the environment, land use, or other factors. Tesla would need to engage in effective stakeholder management, address concerns, and communicate the benefits of the Gigafactory to gain public support. | 2024-04-21 | Russel- General Manager | Open
6 | Sustainability and Environmental Impact: Building and operating a Gigafactory can have significant environmental impacts, such as carbon emissions, water usage, and waste generation, requiring Tesla to implement sustainable practices and mitigate environmental harm. | 2024-04-21 | Steve- EPA | Open

## SH-reg
Stakeholder Register
Name | Org / Dept | Stakeholder Role | Why important? Power/Influence Impact/Interest | How to Engage?
Com | Communities | Resides in area of the new facility; impacted by all the indirect outcomes | Medium- Level of interest varies by the individual and proximity to the location of the facility. Their influence will be via local government. However, they contribute to the skilled labor required | Local town hall meetings for construction related issues College / Trade career fairs for engaging with skilled labor
Cus | Customers | End users who determine demand and products success | Low- Engagement with end product customers is outside scope of this internal company project | Advertisements; outside the scope of the project.
Inv | Investors / Shareholders | Provide the company with capital to fund projects / operations | Medium- Tesla currently has a high level of free cashflow in order to fund this project, however the continued engagement with investors is a key component to the future success of Tesla | CEO / Board of Directors engage with investores and shareholders. Out of scope for project team's level of engagement
Michael | US Department of Agriculture (USDA) | USDA Auditor: Responsible for the approval of development in rural areas and impacts to natrual resources | High- Loction selection is dependant upon the compliance with federal laws/ regulations. Approvals will be required for final location selection | Construction request submittal; potential survey or audit may be conducted by the department. Compliance focal must be assigned
Steve | Environmental Protection Agency (EPA) | EPA Auditor: Responisble for the approval of development based on impacts to environment | High- Loction selection is dependant upon the compliance with federal laws/ regulations. Approvals will be required for final location selection | Construction request submittal; potential survey or audit may be conducted by the department. Compliance focal must be assigned
Richard | Local Government | Governer: Provides bids (grants) to have factory built in their region in order to produce additional jobs and revenue | Medium- Local government can provide grants and tax breaks as an incentive to bring Tesla's new facilitiy to their region | Local town hall meetings and meetings with leadership to secure grant funding
Sup | Suppliers | Provide the material required in order to construct the facility | Medium- Critical aspect of the project will be managed by the supply chain team | Supply chain will have regular, recurring engagement throughout the project until all material has been obtained and is of proper quality
Hannah | 3rd Party Construction | Construction Company Rep: Plan, coordinate, budget, and supervise construction project from start to finish, they monitor project and make decisions about construction activities | High- Project dependant on lead time for constructing the facility | Initial contract negotiations, then weekly project schedule development collaboration. Weekly progress to plan meetings during implementation
Doug | Engineering | Facilities Engineer: Responsible for designing the infrastructure of the facility | High- Design plans will be part of the project's critical path | Primary memeber of project team; weekly recurring meetings + ad hoc as needed
Sven | Operations | Operations Director: Responsible to mapping the layout of the buidling to ensure a lean / optimized value stream | High- Facility layout will be part of the project's critical path | Primary memeber of project team; weekly recurring meetings + ad hoc as needed
Ryan | Finance | Financial Analyst: Provides estimate of project budget in order to seek approval. Track process and deviations | High- Key stakeholder in quantifying capital required and tracking adherence to budget | Primary memeber of project team; weekly recurring meetings + ad hoc as needed
Toyna | HR | HR Generalist: Responsible for hiring and setting up compensation of all new employees required for new facility | Medium- List of skills needed and hiring plan for new facility employees will be part of the project's critical path | Primary memeber of project team; weekly recurring meetings + ad hoc as needed
Camille | Supply Chain | Procurement Agent: Responsible for ordering all material required to complete the construction of the new facility | High- Key stakeholder in securing the material required for the construction of the facility | Primary memeber of project team; weekly recurring meetings + ad hoc as needed
Russel | Automotive General Manager | General Manager: Provides guidance and input on project. Will report up and out to next level of leadership | High- Primary customer of the project. 2nd tier of approval after functions. Next higher layer is CEO & board of directors | Monthly performance to plan report outs. Member of the Change Control Board when seeking additional funding or other resources
BD | Board of Directors | Allocate funding and other resources in order to complete the project | High- Final tier of approval | CEO will engage with Board of Directors
Mary | Regulatory Affairs | Compliance Manager: Resposible for being the liason between Tesla and government regulators to ensure that the selected location and structures are compliant | High- Significant impact to the overall exectution of the project. Goverment permits and approvals are a predicessor to any development / construction implementation | Primary memeber of project team; weekly recurring meetings + ad hoc as needed

## SH-grid
10 | C |  |  |  | BD |  |  |  |  | D
[7 empty] | USDA / EPA | Fin | Eng / Ops / SC | Reg
9
8 |  |  | Inv |  |  |  | GM
Sup / Con
7
HR
6
5
4 | [6 empty] | LG
3
2 |  |  |  |  | Com
Cus
1
| A | [8 empty] | B
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Power
Low
High
Level of Interest
Low
High

## Charter
Project Charter
Project details
Date: | 2024-04-21 | Project #: | 01'
Project manager:
Project name: | Selecting a location to build Tesla’s Gigafactory
I. Vision
Tesla's Gigafactories are large-scale production facilities designed to produce electric vehicle batteries, energy storage systems, and solar products. These factories help Tesla to scale up production and reduce the cost of their products. The Gigafactories in Nevada and China have established a strong foundation, achieving significant return on investment and propelling electric vehicle adoption. To maintain this momentum, we envision building a new Gigafactory strategically located to optimize production efficiency and cost-effectiveness. This next-generation facility will leverage Tesla's existing expertise in large-scale manufacturing while incorporating cutting-edge research in logistics, transportation, and workforce development. Through rigorous site selection, we aim to achieve faster production ramp-up compared to previous facilities, reaching or exceeding established production targets within a shorter timeframe. This strategic expansion will solidify Tesla's leadership in electric vehicle production and accelerate the global transition to sustainable transportation.
II. Objective
Identify and recommend Tesla's Gigafactory location by Mar/31/2026, utilizing a budget of $141,551.
III. Scope
Deliverables: | Project Management | Facility Blueprints (Design) | Site Selection Criteria | Location Selection | Stakeholder Engagement | Permit Approval | Financial Analysis | Project Closure
Measures: | - 100% buyoff from Change Control Board (CCB) - Post sprint project scope reivews | - Percentage utilization of square footage | - Supply Chain Efficiency Index (SCEI) - Community Engagement Score (CES) | - Geographic suitability assessment - Completion of stakeholder consultations within 3 months - Site survey to determine available square footage - Risk assessment KPI's | - Exection of weekly stakeholder reviews - Team effectiveness assessment (TEA) | - Milestone Completion of local, state and federal permits | - ROI - Budget utilization - Execution of weekly budget review | - Schedule Baseline Execution Index (BEI)
Exclusions: | - Detailed construction plan | - Bill of Materials list (BOM) - Electrical / Plumbing details | - Locations with Limited Access to Renewable Energy Sources. - Areas with Unfavorable Regulatory Environments - Procurement of material | - Avoid areas lacking essential infrastructure (e.g., transportation, utilities) - Avoid areas with insufficient skilled labor or high labor costs | - Post location selection, external stakeholder engagement | - Post Site Selection Permit Fees - Future Mitigatoin Plan for Regulatory Changes | - Risk / sensitivity analysis | - Oversight of construction execution - Oversight of site procurement

## Prio-BLog (hidden)
Prioritized Backlog
Value-Risk-Dependencies
1
2
3
4
5
6
7
8
9
10

## Cost Estimate
b | PROJECT COST ESTIMATE
Assumptions:
1. Labor cost is calculated by applying the total hours for each task, multiplied by the specific labor rate of each contributor, found in the RMatrix table
2. As construction is out of scope for the project, no material costs are required. Therefore, total cost will be calculated by the sum of the overall labor
3. Final budget approval will be taken through all phases of the change control board (CCB) to ensure internal stakeholder / leadership approval
[7 empty] | BUDGET | ACTUAL | UNDER/OVER
[7 empty] | 143390.5 | 0 | 0
|  | LABOR |  | MATERIALS |  | NON-LABOR | BUDGET | ACTUAL | UNDER/OVER
| TASK | HRS | RATE | UNITS | $/UNIT
Project Management
| Create Project Scope & Objectives | 44 | 50.34 |  |  |  | 2214.96 |  | -2214.96
| Identify Key Stakeholders | 31 | 47.74 |  |  |  | 1479.94 |  | -1479.94
| Establish Timeline & Budget | 28 | 54.82 |  |  |  | 1534.96 |  | -1534.96
| Develop Communication Cadence | 21 | 49.9 |  |  |  | 1047.9 |  | -1047.9
[7 empty] | 6277.76 | 0
Facility Blueprints (Design)
| Create Site Layout | 36 | 33 |  |  |  | 1188 |  | -1188
| Confirm Square Footage | 6 | 49.3333 |  |  |  | 296 |  | -296
| Draft Blueprint | 23 | 48.3478 |  |  |  | 1112 |  | -1112
| Obtain LEED Approval | 18 | 46.3889 |  |  | 2000 | 835 |  | -835
[7 empty] | 5431 | 0
Site Selection Criteria
| Quantify Desired Proximity to Raw Materials | 20 | 51.25 |  |  | 10000 | 1025 |  | -1025
| Quantify Desired Proximity to Renewable Energy Sources | 25 | 32.2 |  |  | 10000 | 805 |  | -805
| Document Skilled Workforce Criteria | 45 | 48.6667 |  |  | - | 2190 |  | -2190
| Create Infrastructure and Logistics Criteria | 25 | 48 |  |  | - | 1200 |  | -1200
| Outline Regulatory Environment | 15 | 47.3333 |  |  | - | 710 |  | -710
| List Environmental Impact and Sustainability | 39 | 47.1795 |  |  | - | 1840 |  | -1840
[7 empty] | 27770 | 0
Location Selection
| Formulate Site Selection Report | 40 | 48.125 |  |  | - | 1925 |  | -1925
| Create Cost-Benefit Analysis | 50 | 50.5 |  |  | - | 2525 |  | -2525
| Develop Risk Assessment report | 55 | 48.3636 |  |  | 5000 | 2660 |  | -2660
[7 empty] | 12110 | 0
Stakeholder Engagement
| Attend Local Townhall Meetings | 33 | 52.1212 |  |  | 1500 | 1720 |  | -1720
| Identify Neighboring University & Trade School Partnership | 49 | 49.898 |  |  | 1500 | 2445 |  | -2445
| Secure USDA & EPA Partnership | 17 | 48.9412 |  |  |  | 832 |  | -832
| Establish Review Cadence with Engineering and Supply Chain | 29 | 47.4138 |  |  |  | 1375 |  | -1375
[7 empty] | 9372 | 0
Permit Approval
| Identify and Secure Federal Permits | 12 | 52.0833 |  |  | 4000 | 625 |  | -625
| Identify and Secure State Permints | 12 | 52.0833 |  |  | 2000 | 625 |  | -625
| Identify and Secure County Permits | 12 | 52.0833 |  |  | 1500 | 625 |  | -625
| Identify Recurring Permit Requirements | 12 | 52.0833 |  |  |  | 625 |  | -625
[7 empty] | 10000 | 0
Financial Analysis
| Estimate construction costs & operating expenses | 51 | 50.6471 |  |  |  | 2583 |  | -2583
| Document Tax Benefits for Each Location | 18 | 52.8889 |  |  |  | 952 |  | -952
| Develop Financial Model | 17 | 51.7059 |  |  |  | 879 |  | -879
[7 empty] | 4414 | 0
Project Closure
| Document lessons learned | 38 | 50.63 |  |  |  | 1923.94 |  | -1923.94
| Finalize project deliverables and reports | 38 | 51.1 |  |  |  | 1941.8 |  | -1941.8
| Submit Final Deliverables | 3 | 50 |  |  |  | 150 |  | -150
[7 empty] | 4015.74 | 0
| Risk Mitigation / Buffer |  |  |  |  | 64000 | 64000 |  | -64000
| TOTAL | [5 empty] | 143390.5 | 0
| Team Member | Hourly Rate
| Doug Engineering | 45
| Sven Operations Director | 50
| Ryan Finance | 55
| Tonya HR | 47
| Camille Supply Chain | 45
| Russel Automotive GM | 65
| Mary Compliance Manager | 46
| PM | 50

## Risk
|  | Risk Description | Probability | Impact | Prob x Impact | Response (choose) | Action | Cost
|  | Failure to secure local suppliers and logistics. | 3 | 5 | 15 | Mitigate | Send a wider reaching request for proposal (RFP) for prospective suppliers | 1000
|  | Failure to secure the proper permits in order to remain compliant and allow for consturction | 4 | 4 | 16 | Mitigate | Assign a compliance focal to prioritize all permit approvals | 1000
|  | Failure to secure skilled labor | 3 | 3 | 9 | Transfer | HR to secure partnerships with neighboring universities and trade schools to ensure a talent pipeline for the new facility | 10000
|  | Ineffieicent access to energy infrastructure | 1 | 4 | 4 | Accept | Energy proximity criteria built into plan
|  | Changes in market demand for electric vehicles | 2 | 5 | 10 | Accept | Conduct thorough market analysis and maintain flexibility in production capabilities are important.
|  | Financial mismanagement | 5 | 5 | 25 | Avoid | Ensure accurate cost estimation, secure sufficient funding, and manage cash flow. Add $50,000 to buffer for budget deviation. | 50000
|  | Unexpected public pushback from local communities and environmental groups. | 3 | 3 | 9 | Mitigate | Extensive community engagement to address concerns and gather public support for the project | 2000
|  | Project not approved by Tesla's internal investment board | 3 | 5 | 15 | Accept | Create a comprehensive analysis for the board to consider all variables
64000
Total Risks | 7 | * If X occurs during the project, then Y is the impact (on CSP), and Z is the result. (Impact on the project or business).
If the team fails to secure local suppliers during the project, then the flow of materials will be impacted, and a longer production lead time is the result.
7 | If the team fails to secure the proper permits for construction, then the company will be impacted by fines as a result.
If the team fails to identify skilled labor to staff the site, then the site will have poor quality output, resulting in increase to COGS and lead time
If the team fails to identify the proper access to engergy infrastructure, then construction will be delayed, resulting in additional costs and schedule slides
If the damand for electric vehicles decreases, then there is less of a demand for an additional location, resulting in a canceled project.
If the budget is not managed properly, additional dollars maybe required, resulting in additional costs for Tesla.
If the local community does not welcome the new facility, then operations may be impacted, resulting in delays to prodction and delivery.

## WBS
|  | Project Management |  | Facility Blueprints (Design) |  | Site Selection Criteria |  | Location Selection |  | Stakeholder Engagement |  | Permit Approval |  | Financial Analysis |  | Project Closure |  | #REF! |  | #REF! |  | #REF!
|  | #REF! |  | #REF! |  | #REF! |  | #REF! |  |  |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
|  | #REF! |  | #REF! |  | #REF! |  | #REF! |  |  |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
Project: Tesla Gigafactory Location
Deliverables | 1.0 | Project Management | 2.0 | Facility Blueprints (Design) | 3.0 | Site Selection Criteria | 4.0 | Location Selection | 5.0 | Stakeholder Engagement | 6.0 | Permit Approval | 7.0 | Financial Analysis | 8.0 | Project Closure | 8.0 | #8 Priority deliver. | 9.0 | #9 Priority deliver. | 10.0 | #10 Priority deliver. | 11.0 | #11 Priority deliver. | 12.0 | #12 Priority deliver. | 13.0 | #13 Priority deliver. | 14.0 | #14 Priority deliver. | 15.0 | #15 Priority deliver. | 16.0 | #16 Priority deliver. | 17.0 | #17 Priority deliver. | 18.0 | #18 Priority deliver. | 19.0 | #19 Priority deliver. | 20.0 | #20 Priority deliver. | 21.0 | #21 Priority deliver. | 22.0 | #22 Priority deliver. | 23.0 | #23 Priority deliver. | 24.0 | #24 Priority deliver. | 25.0 | #25 Priority deliver. | 26.0 | #26 Priority deliver. | 27.0 | #27 Priority deliver. | 28.0 | #28 Priority deliver. | 29.0 | #29 Priority deliver. | 30.0 | #30 Priority deliver.
Tasks Tasksmust be a verb+noun combination in order to convey action | 1.01 | Create Project Scope & Objectives | 2.01 | Create Site Layout | 3.01 | Quantify Desired Proximity to Raw Materials | 4.01 | Formulate Site Selection Report | 5.01 | Attend Local Townhall Meetings | 6.01 | Identify and Secure Federal Permits | 7.01 | Estimate construction costs & operating expenses | 8.01 | Document lessons learned | 8.01 | Task 01 | 9.1 | Task 01 | 10.1 | Task 01 | 11.1 | Task 01 | 12.1 | Task 01 | 13.1 | Task 01 | 14.1 | Task 01 | 15.1 | Task 01 | 15.1 | Task 01 | 17.1 | Task 01 | 18.1 | Task 01 | 19.1 | Task 01 | 20.1 | Task 01 | 21.1 | Task 01 | 22.1 | Task 01 | 23.1 | Task 01 | 24.1 | Task 01 | 25.1 | Task 01 | 26.1 | Task 01 | 27.1 | Task 01 | 28.1 | Task 01 | 29.1 | Task 01 | 30.1 | Task 01
| 1.02 | Identify Key Stakeholders | 2.02 | Confirm Square Footage | 3.02 | Quantify Desired Proximity to Renewable Energy Sources | 4.02 | Create Cost-Benefit Analysis | 5.02 | Identify Neighboring University & Trade School Partnership | 6.02 | Identify and Secure State Permints | 7.02 | Document Tax Benefits for Each Location | 8.02 | Finalize project deliverables and reports | 8.02 | Task 02 | 9.2 | Task 02 | 10.2 | Task 02 | 11.2 | Task 02 | 12.2 | Task 02 | 13.2 | Task 02 | 14.2 | Task 02 | 15.2 | Task 02 | 15.2 | Task 02 | 17.2 | Task 02 | 18.2 | Task 02 | 19.2 | Task 02 | 20.2 | Task 02 | 21.2 | Task 02 | 22.2 | Task 02 | 23.2 | Task 02 | 24.2 | Task 02 | 25.2 | Task 02 | 26.2 | Task 02 | 27.2 | Task 02 | 28.2 | Task 02 | 29.2 | Task 02 | 30.2 | Task 02
| 1.03 | Establish Timeline & Budget | 2.03 | Draft Blueprint | 3.03 | Document Skilled Workforce Criteria | 4.03 | Develop Risk Assessment report | 5.03 | Secure USDA & EPA Partnership | 6.03 | Identify and Secure County Permits | 7.03 | Develop Financial Model | 8.03 | Submit Final Deliverables | 8.03 | Task 03 | 9.3 | Task 03 | 10.3 | Task 03 | 11.3 | Task 03 | 12.3 | Task 03 | 13.3 | Task 03 | 14.3 | Task 03 | 15.3 | Task 03 | 15.3 | Task 03 | 17.3 | Task 03 | 18.3 | Task 03 | 19.3 | Task 03 | 20.3 | Task 03 | 21.3 | Task 03 | 22.3 | Task 03 | 23.3 | Task 03 | 24.3 | Task 03 | 25.3 | Task 03 | 26.3 | Task 03 | 27.3 | Task 03 | 28.3 | Task 03 | 29.3 | Task 03 | 30.3 | Task 03
| 1.04 | Develop Communication Cadence | 2.04 | Obtain LEED Approval | 3.04 | Create Infrastructure and Logistics Criteria |  |  | 5.04 | Establish Review Cadence with Engineering and Supply Chain | 6.04 | Identify Recurring Permit Requirements |  |  |  |  | 8.04 | Task 04 | 9.4 | Task 04 | 10.4 | Task 04 | 11.4 | Task 04 | 12.4 | Task 04 | 13.4 | Task 04 | 14.4 | Task 04 | 15.4 | Task 04 | 15.4 | Task 04 | 17.4 | Task 04 | 18.4 | Task 04 | 19.4 | Task 04 | 20.4 | Task 04 | 21.4 | Task 04 | 22.4 | Task 04 | 23.4 | Task 04 | 24.4 | Task 04 | 25.4 | Task 04 | 26.4 | Task 04 | 27.4 | Task 04 | 28.4 | Task 04 | 29.4 | Task 04 | 30.4 | Task 04
[5 empty] | 3.05 | Outline Regulatory Environment | [10 empty] | 8.05 | Task 05 | 9.5 | Task 05 | 10.5 | Task 05 | 11.5 | Task 05 | 12.5 | Task 05 | 13.5 | Task 05 | 14.5 | Task 05 | 15.5 | Task 05 | 15.5 | Task 05 | 17.5 | Task 05 | 18.5 | Task 05 | 19.5 | Task 05 | 20.5 | Task 05 | 21.5 | Task 05 | 22.5 | Task 05 | 23.5 | Task 05 | 24.5 | Task 05 | 25.5 | Task 05 | 26.5 | Task 05 | 27.5 | Task 05 | 28.5 | Task 05 | 29.5 | Task 05 | 30.5 | Task 05
[5 empty] | 3.06 | List Environmental Impact and Sustainability | [10 empty] | 8.06 | Task 06 | 9.6 | Task 06 | 10.6 | Task 06 | 11.6 | Task 06 | 12.6 | Task 06 | 13.6 | Task 06 | 14.6 | Task 06 | 15.6 | Task 06 | 15.6 | Task 06 | 17.6 | Task 06 | 18.6 | Task 06 | 19.6 | Task 06 | 20.6 | Task 06 | 21.6 | Task 06 | 22.6 | Task 06 | 23.6 | Task 06 | 24.6 | Task 06 | 25.6 | Task 06 | 26.6 | Task 06 | 27.6 | Task 06 | 28.6 | Task 06 | 29.6 | Task 06 | 30.6 | Task 06
[17 empty] | 8.07 | Task 07 | 9.7 | Task 07 | 10.7 | Task 07 | 11.7 | Task 07 | 12.7 | Task 07 | 13.7 | Task 07 | 14.7 | Task 07 | 15.7 | Task 07 | 15.7 | Task 07 | 17.7 | Task 07 | 18.7 | Task 07 | 19.7 | Task 07 | 20.7 | Task 07 | 21.7 | Task 07 | 22.7 | Task 07 | 23.7 | Task 07 | 24.7 | Task 07 | 25.7 | Task 07 | 26.7 | Task 07 | 27.7 | Task 07 | 28.7 | Task 07 | 29.7 | Task 07 | 30.7 | Task 07
| 1.08 |  | 2.08 |  | 3.08 |  | 4.08 |  |  |  | 5.08 |  | 6.08 |  | 7.08 |  | 8.08 | Task 08 | 9.8 | Task 08 | 10.8 | Task 08 | 11.8 | Task 08 | 12.8 | Task 08 | 13.8 | Task 08 | 14.8 | Task 08 | 15.8 | Task 08 | 15.8 | Task 08 | 17.8 | Task 08 | 18.8 | Task 08 | 19.8 | Task 08 | 20.8 | Task 08 | 21.8 | Task 08 | 22.8 | Task 08 | 23.8 | Task 08 | 24.8 | Task 08 | 25.8 | Task 08 | 26.8 | Task 08 | 27.8 | Task 08 | 28.8 | Task 08 | 29.8 | Task 08 | 30.8 | Task 08
| 1.09 |  | 2.09 |  | 3.09 |  | 4.09 |  |  |  | 5.09 |  | 6.09 |  | 7.09 |  | 8.09 | Task 09 | 9.9 | Task 09 | 10.9 | Task 09 | 11.9 | Task 09 | 12.9 | Task 09 | 13.9 | Task 09 | 14.9 | Task 09 | 15.9 | Task 09 | 15.9 | Task 09 | 17.9 | Task 09 | 18.9 | Task 09 | 19.9 | Task 09 | 20.9 | Task 09 | 21.9 | Task 09 | 22.9 | Task 09 | 23.9 | Task 09 | 24.9 | Task 09 | 25.9 | Task 09 | 26.9 | Task 09 | 27.9 | Task 09 | 28.9 | Task 09 | 29.9 | Task 09 | 30.9 | Task 09
| 1.10 |  | 2.10 |  | 3.10 |  | 4.10 |  |  |  | 5.10 |  | 6.10 |  | 7.10 |  | 8.10 | Task 10 | 9.10 | Task 10 | 10.10 | Task 10 | 11.10 | Task 10 | 12.10 | Task 10 | 13.10 | Task 10 | 14.10 | Task 10 | 15.10 | Task 10 | 15.10 | Task 10 | 17.10 | Task 10 | 18.10 | Task 10 | 19.10 | Task 10 | 20.10 | Task 10 | 21.1 | Task 10 | 22.1 | Task 10 | 23.1 | Task 10 | 24.1 | Task 10 | 25.1 | Task 10 | 26.1 | Task 10 | 27.1 | Task 10 | 28.1 | Task 10 | 29.1 | Task 10 | 30.1 | Task 10
| 1.11 |  | 2.11 |  | 3.11 |  | 4.11 |  |  |  | 5.11 |  | 6.11 |  | 7.11 |  | 8.11 | Task 11 | 9.11 | Task 11 | 10.11 | Task 11 | 11.11 | Task 11 | 12.11 | Task 11 | 13.11 | Task 11 | 14.11 | Task 11 | 15.11 | Task 11 | 15.11 | Task 11 | 17.11 | Task 11 | 18.11 | Task 11 | 19.11 | Task 11 | 20.11 | Task 11 | 21.11 | Task 11 | 22.11 | Task 11 | 23.11 | Task 11 | 24.11 | Task 11 | 25.11 | Task 11 | 26.11 | Task 11 | 27.11 | Task 11 | 28.11 | Task 11 | 29.11 | Task 11 | 30.11 | Task 11
| 1.12 |  | 2.12 |  | 3.12 |  | 4.12 |  |  |  | 5.12 |  | 6.12 |  | 7.12 |  | 8.12 | Task 12 | 9.12 | Task 12 | 10.12 | Task 12 | 11.12 | Task 12 | 12.12 | Task 12 | 13.12 | Task 12 | 14.12 | Task 12 | 15.12 | Task 12 | 15.12 | Task 12 | 17.12 | Task 12 | 18.12 | Task 12 | 19.12 | Task 12 | 20.12 | Task 12 | 21.12 | Task 12 | 22.12 | Task 12 | 23.12 | Task 12 | 24.12 | Task 12 | 25.12 | Task 12 | 26.12 | Task 12 | 27.12 | Task 12 | 28.12 | Task 12 | 29.12 | Task 12 | 30.12 | Task 12
| 1.13 |  | 2.13 |  | 3.13 |  | 4.13 |  |  |  | 5.13 |  | 6.13 |  | 7.13 |  | 8.13 | Task 13 | 9.13 | Task 13 | 10.13 | Task 13 | 11.13 | Task 13 | 12.13 | Task 13 | 13.13 | Task 13 | 14.13 | Task 13 | 15.13 | Task 13 | 15.13 | Task 13 | 17.13 | Task 13 | 18.13 | Task 13 | 19.13 | Task 13 | 20.13 | Task 13 | 21.13 | Task 13 | 22.13 | Task 13 | 23.13 | Task 13 | 24.13 | Task 13 | 25.13 | Task 13 | 26.13 | Task 13 | 27.13 | Task 13 | 28.13 | Task 13 | 29.13 | Task 13 | 30.13 | Task 13
| 1.14 |  | 2.14 |  | 3.14 |  | 4.14 |  |  |  | 5.14 |  | 6.14 |  | 7.14 |  | 8.14 | Task 14 | 9.14 | Task 14 | 10.14 | Task 14 | 11.14 | Task 14 | 12.14 | Task 14 | 13.14 | Task 14 | 14.14 | Task 14 | 15.14 | Task 14 | 15.14 | Task 14 | 17.14 | Task 14 | 18.14 | Task 14 | 19.14 | Task 14 | 20.14 | Task 14 | 21.14 | Task 14 | 22.14 | Task 14 | 23.14 | Task 14 | 24.14 | Task 14 | 25.14 | Task 14 | 26.14 | Task 14 | 27.14 | Task 14 | 28.14 | Task 14 | 29.14 | Task 14 | 30.14 | Task 14
| 1.15 |  | 2.15 |  | 3.15 |  | 4.15 |  |  |  | 5.15 |  | 6.15 |  | 7.15 |  | 8.15 | Task 15 | 9.15 | Task 15 | 10.15 | Task 15 | 11.15 | Task 15 | 12.15 | Task 15 | 13.15 | Task 15 | 14.15 | Task 15 | 15.15 | Task 15 | 15.15 | Task 15 | 17.15 | Task 15 | 18.15 | Task 15 | 19.15 | Task 15 | 20.15 | Task 15 | 21.15 | Task 15 | 22.15 | Task 15 | 23.15 | Task 15 | 24.15 | Task 15 | 25.15 | Task 15 | 26.15 | Task 15 | 27.15 | Task 15 | 28.15 | Task 15 | 29.15 | Task 15 | 30.15 | Task 15
ES Dur EF
Task #
LS Float LF
4 6 9
Task B
|  | 1 3 3 |  | 4 6 9
Task A
1 3 3
4 3 6
Task C
7 3 9

## RMatrix
Being played today by... |  | R (esponsible) OR C (ontributor) | [58 empty] | C or R
| Name + Dept. | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate | C or R | Estimate
| Doug Engineering | C | 5 | C | 4 |  |  | C | [23 empty] | R | 15 | R | 3 | R | 15 | C | 5 | [23 empty] | R | 10 | C | 5 | R | 10 |  |  | C | 7 | [18 empty] | C | 5 | C | 10 | C | 10 | [26 empty] | C | 4 |  |  | C | 10 | [50 empty] | C | 10 |  |  | C | 2 | [24 empty] | C | 3 | C | 3
| Sven Operations Director | C | 6 | C | 6 | C | 5 | C | 3 | [22 empty] | C | 10 | [31 empty] | C | 5 | C | 5 |  |  | C | 5 | [18 empty] | C | 2 | C | 5 | C | 5 | [24 empty] | C | 6 | C | 4 | [54 empty] | C | 10 | C | 2 | C | 2 | [24 empty] | C | 3 | C | 3
| Ryan Finance |  |  |  |  | R | 12 | C | 2 | [55 empty] | C | 10 | C | 5 | [22 empty] | C | 3 | R | 20 | C | 5 | [26 empty] | C | 3 | [54 empty] | R | 15 | R | 5 | R | 5 | [24 empty] | C | 3 | C | 3
| Tonya HR | [63 empty] | R | 20 | [56 empty] | R | 20 | [56 empty] | C | 2 | C | 2 | [24 empty] | C | 3 | C | 2
| Camille Supply Chain | C | 6 | C | 6 |  |  | C | 3 | [22 empty] | C | 5 | [27 empty] | R | 10 |  |  | C | 5 | C | 5 |  |  | C | 7 | [18 empty] | C | 5 | C | 5 | C | 5 | [26 empty] | C | 3 |  |  | C | 5 | [50 empty] | C | 5 |  |  | C | 2 | [24 empty] | C | 3 | C | 3
| Russel Automotive GM | C | 6 |  |  | C | 5 | C | 2 | [24 empty] | C | 1 | C | 3 | [23 empty] | C | 5 | C | 5 | [56 empty] | C | 6 | C | 5 | C | 2 | [22 empty] | C | 3 | C | 3 | C | 3 | C | 3 | [22 empty] | C | 3 | C | 3 | C | 2 | [24 empty] | C | 4 | C | 5
| Mary Compliance Manager | C | 5 | C | 5 |  |  | C | 3 | [22 empty] | C | 3 | C | 1 | C | 2 | R | 10 | [23 empty] | C | 5 |  |  |  |  | R | 10 | R | 10 | [18 empty] | C | 10 |  |  | C | 10 | [24 empty] | R | 5 |  |  | R | 12 | [22 empty] | R | 5 | R | 5 | R | 5 | R | 5 | [22 empty] | C | 3 | C | 3 | [26 empty] | C | 3 | C | 3
| Tyler PM | R | 16 | R | 10 | C | 6 | R | 5 | [22 empty] | C | 3 | C | 1 | C | 3 | C | 3 | [21 empty] | C | 5 | C | 5 |  |  |  |  | C | 5 | C | 10 | [18 empty] | R | 15 | C | 10 | R | 20 | [24 empty] | C | 16 | C | 10 | C | 3 | R | 14 | [20 empty] | C | 4 | C | 4 | C | 4 | C | 4 | [22 empty] | C | 5 | C | 3 | C | 2 | [24 empty] | R | 16 | R | 16 | R | 3
| Tasks | Create Project Scope & Objectives | 44 | Identify Key Stakeholders | 31 | Establish Timeline & Budget | 28 | Develop Communication Cadence | 18 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Create Site Layout | 36 | Confirm Square Footage | 6 | Draft Blueprint | 23 | Obtain LEED Approval | 18 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | Quantify Desired Proximity to Raw Materials | 20 | Quantify Desired Proximity to Renewable Energy Sources | 25 | Document Skilled Workforce Criteria | 45 | Create Infrastructure and Logistics Criteria | 25 | Outline Regulatory Environment | 15 | List Environmental Impact and Sustainability | 39 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Formulate Site Selection Report | 40 | Create Cost-Benefit Analysis | 50 | Develop Risk Assessment report | 55 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Attend Local Townhall Meetings | 33 | Identify Neighboring University & Trade School Partnership | 49 | Secure USDA & EPA Partnership | 17 | Establish Review Cadence with Engineering and Supply Chain | 29 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Identify and Secure Federal Permits | 12 | Identify and Secure State Permints | 12 | Identify and Secure County Permits | 12 | Identify Recurring Permit Requirements | 12 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Estimate construction costs & operating expenses | 51 | Document Tax Benefits for Each Location | 18 | Develop Financial Model | 17 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Document lessons learned | 38 | Finalize project deliverables and reports | 38 | Submit FInal Deliverables | 3 | Task 04 | 0 | Task 05 | 0 | Task 06 | 0 | Task 07 | 0 | Task 08 | 0 | Task 09 | 0 | Task 10 | 0 | Task 11 | 0 | Task 12 | 0 | Task 13 | 0 | Task 14 | 0 | Task 15 | 0 | Task 01 | 0 | Task 02 | 0 | Task 03 | 0 | Task 04 | 0 | Task 06 | 0 | Task 07 | 0 | Task 08 | 0 | Task 10 | 0 | Task 11 | 0 | Task 12 | 0 | Task 13 | 0 | Task 14 | 0 | Task 15 | 0 | Task 01 | 0 | Task 02 | 0 | Task 03 | 0 | Task 04 | 0 | Task 05 | 0 | Task 06 | 0 | Task 07 | 0 | Task 08 | 0 | Task 09 | 0 | Task 10 | 0 | Task 11 | 0 | Task 12 | 0 | Task 13 | 0 | Task 14 | 0 | Task 15 | 0 | Task 01 | 0 | Task 02 | 0 | Task 03 | 0 | Task 04 | 0 | Task 05 | 0 | Task 06 | 0 | Task 07 | 0 | Task 08 | 0 | Task 09 | 0 | Task 10 | 0 | Task 11 | 0 | Task 12 | 0 | Task 13 | 0 | Task 14 | 0 | Task 15 | 0 | Task 01 | 0 | Task 02 | 0 | Task 03 | 0 | Task 04 | 0 | Task 05 | 0 | Task 06 | 0 | Task 07 | 0 | Task 08 | 0 | Task 09 | 0 | Task 10 | 0 | Task 11 | 0 | Task 12 | 0 | Task 13 | 0 | Task 14 | 0 | Task 15 | 0 | Task 01 | 0 | Task 02 | 0 | Task 03 | 0 | Task 04 | 0 | Task 05 | 0 | Task 06 | 0 | Task 07 | 0 | Task 08 | 0 | Task 09 | 0 | Task 10 | 0 | Task 11 | 0 | Task 12 | 0 | Task 13 | 0 | Task 14 | 0 | Task 15 | 0 | Task 01 | 0 | Task 02 | 0 | Task 03 | 0 | Task 04 | 0 | Task 05 | 0 | Task 06 | 0 | Task 07 | 0 | Task 08 | 0 | Task 09 | 0 | Task 10 | 0 | Task 11 | 0 | Task 12 | 0 | Task 13 | 0 | Task 14 | 0 | Task 15 | 0 | Task 01 | 0 | Task 02 | 0 | Task 03 | 0 | Task 04 | 0 | Task 05 | 0 | Task 06 | 0 | Task 07 | 0 | Task 08 | 0 | Task 09 | 0 | Task 10 | 0 | Task 11 | 0 | Task 12 | 0 | Task 13 | 0 | Task 14 | 0 | Task 15 | 0 | Task 01 | 0 | Task 02 | 0 | Task 03 | 0 | Task 04 | 0 | Task 05 | 0 | Task 06 | 0 | Task 07 | 0 | Task 08 | 0 | Task 09 | 0 | Task 10 | 0 | Task 11 | 0 | Task 12 | 0 | Task 13 | 0 | Task 14 | 0 | Task 15 | 0 | Task 01 | 0 | Task 02 | 0 | Task 03 | 0 | Task 04 | 0 | Task 05 | 0 | Task 06 | 0 | Task 07 | 0 | Task 08 | 0 | Task 09 | 0 | Task 10 | 0 | Task 11 | 0 | Task 12 | 0 | Task 13 | 0 | Task 14 | 0 | Task 15 | 0 | Task 01 | 0 | Task 02 | 0 | Task 03 | 0 | Task 04 | 0 | Task 05 | 0 | Task 06 | 0 | Task 07 | 0 | Task 08 | 0 | Task 09 | 0 | Task 10 | 0 | Task 11 | 0 | Task 12 | 0 | Task 13 | 0 | Task 14 | 0 | Task 15 | 0 | Task 01 | 0 | Task 02 | 0 | Task 03 | 0 | Task 04 | 0 | Task 05 | 0 | Task 06 | 0 | Task 07 | 0 | Task 08 | 0 | Task 10 | 0 | Task 11 | 0 | Task 12 | 0 | Task 13 | 0 | Task 14 | 0 | Task 15 | 0 | Task 01 | 0 | Task 02 | 0 | Task 03 | 0 | Task 04 | 0 | Task 05 | 0 | Task 06 | 0 | Task 07 | 0 | Task 08 | 0 | Task 09 | 0 | Task 10 | 0 | Task 11 | 0 | Task 12 | 0 | Task 13 | 0 | Task 14 | 0 | Task 15 | 0 | Task 01 | 0 | Task 02 | 0 | Task 03 | 0 | Task 04 | 0 | Task 05 | 0 | Task 06 | 0 | Task 07 | 0 | Task 08 | 0 | Task 09 | 0 | Task 10 | 0 | Task 11 | 0 | Task 12 | 0 | Task 13 | 0 | Task 14 | 0 | Task 15 | 0 | Task 01 | 0 | Task 02 | 0 | Task 03 | 0 | Task 04 | 0 | Task 05 | 0 | Task 06 | 0 | Task 07 | 0 | Task 08 | 0 | Task 09 | 0 | Task 10 | 0 | Task 11 | 0 | Task 12 | 0 | Task 13 | 0 | Task 14 | 0 | Task 15 | 0 | Task 01 | 0 | Task 02 | 0 | Task 03 | 0 | Task 04 | 0 | Task 05 | 0 | Task 06 | 0 | Task 07 | 0 | Task 08 | 0 | Task 09 | 0 | Task 10 | 0 | Task 11 | 0 | Task 12 | 0 | Task 13 | 0 | Task 14 | 0 | Task 01 | 0 | Task 02 | 0 | Task 03 | 0 | Task 04 | 0 | Task 05 | 0 | Task 06 | 0 | Task 07 | 0 | Task 08 | 0 | Task 09 | 0 | Task 10 | 0 | Task 11 | 0 | Task 12 | 0 | Task 13 | 0 | Task 14 | 0 | Task 15 | 0 | Task 01 | 0 | Task 02 | 0 | Task 03 | 0 | Task 04 | 0 | Task 05 | 0 | Task 06 | 0 | Task 07 | 0 | Task 08 | 0 | Task 09 | 0 | Task 10 | 0 | Task 11 | 0 | Task 12 | 0 | Task 13 | 0 | Task 14 | 0 | Task 15 | 0 | Task 01 | 0 | Task 02 | 0 | Task 03 | 0 | Task 04 | 0 | Task 05 | 0 | Task 06 | 0 | Task 07 | 0 | Task 08 | 0 | Task 09 | 0 | Task 10 | 0 | Task 11 | 0 | Task 12 | 0 | Task 13 | 0 | Task 14 | 0 | Task 15 | 0 | Task 01 | 0 | Task 02 | 0 | Task 03 | 0 | Task 04 | 0 | Task 05 | 0 | Task 06 | 0 | Task 07 | 0 | Task 08 | 0 | Task 09 | 0 | Task 10 | 0 | Task 11 | 0 | Task 12 | 0 | Task 13 | 0 | Task 14 | 0 | Task 15 | 0 | Task 01 | 0 | Task 02 | 0 | Task 03 | 0 | Task 04 | 0 | Task 05 | 0 | Task 06 | 0 | Task 07 | 0 | Task 08 | 0 | Task 09 | 0 | Task 10 | 0 | Task 11 | 0 | Task 12 | 0 | Task 13 | 0 | Task 14 | 0 | Task 15 | 0 | Task 01 | 0 | Task 02 | 0 | Task 03 | 0 | Task 04 | 0 | Task 05 | 0 | Task 06 | 0 | Task 07 | 0 | Task 08 | 0 | Task 09 | 0 | Task 10 | 0 | Task 11 | 0 | Task 12 | 0 | Task 13 | 0 | Task 14 | 0 | Task 15 | 0 | Task 01 | 0 | Task 02 | 0 | Task 03 | 0 | Task 04 | 0 | Task 05 | 0 | Task 06 | 0 | Task 07 | 0 | Task 08 | 0 | Task 09 | 0 | Task 10 | 0 | Task 11 | 0 | Task 12 | 0 | Task 13 | 0 | Task 14 | 0 | Task 15 | 0
Maybe not
| Deliverables | Project Management | [29 empty] | Facility Blueprints (Design) | [28 empty] | Site Selection Criteria | [29 empty] | Location Selection | [29 empty] | Stakeholder Engagement | [27 empty] | Permit Approval | [29 empty] | Financial Analysis | [29 empty] | Project Closure | [29 empty] | #9 Priority deliver. | [25 empty] | #10 Priority deliver. | [29 empty] | #11 Priority deliver. | [29 empty] | #12 Priority deliver. | [29 empty] | #13 Priority deliver. | [29 empty] | #14 Priority deliver. | [29 empty] | #15 Priority deliver. | [29 empty] | #16 Priority deliver. | [29 empty] | #17 Priority deliver. | [29 empty] | #18 Priority deliver. | [29 empty] | #19 Priority deliver. | [27 empty] | #20 Priority deliver. | [29 empty] | #21 Priority deliver. | [29 empty] | #22 Priority deliver. | [29 empty] | #23 Priority deliver. | [27 empty] | #24 Priority deliver. | [29 empty] | #25 Priority deliver. | [29 empty] | #26 Priority deliver. | [29 empty] | #27 Priority deliver. | [29 empty] | #28 Priority deliver. | [29 empty] | #29 Priority deliver. | [29 empty] | #30 Priority deliver.
[61 empty] | Resource | Hourly Rate
[61 empty] | Doug Engineering | 45 | [184 empty] | Task 13
[61 empty] | Sven Operations Director | 50 | [184 empty] | Task 14
[61 empty] | Ryan Finance | 55
[61 empty] | Tonya HR | 47
[61 empty] | Camille Supply Chain | 45
[61 empty] | Russel Automotive GM | 65
[61 empty] | Mary Compliance Manager | 46
[61 empty] | Avg | 50

## Retro (hidden)
RETROSPECTIVE
WIND |  |  | IDEAS
What gave our team momentum or pushed us to produce the plan? |  | Where and what gave our team ideas and how might they have been used
Comping up with WBS and Stakeholder register helped us get a big picture of the project and we were easily able to navigate further. |  | Industry case study gave a clear scope of where the project was heading towards
Real-World Application where the project is being currently pursued by Tesla made the project more intresting |  | Developed financial models to forecast construction costs, operating expenses, and long-term economic benefits.
Where did we stall out, lose ground or get hung up? |  | When did the monsters arrive and in what form?
We initially came up with a budget of $10 million and eventually realised that the budget would be a lot lesser and had to change it accordingly. |  | For the resource loading table, we needed data from time phased budget and Rmatrix which was a bit challenging in terms of time it took to complete.
There were challenges in collecting real world financial data for accuracy to verify and fill in the gaps |  | Initial scope planning or the planning phase caused dealays
Significant time was spent verifying and cross referencing data which slowed down the evaluation process.
ANCHORS |  |  | MONSTERS

## Schedule
[8 empty] | June |  |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  | Febuary |  |  |  | March |  |  |  | April |  |  |  | May
Task # | Task / Deliverable | Duration (m-days) | Start | Finish | Predecessor | Successor | Resource | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4
1 | Project Management |  | 2024-06-03 | 2024-06-21
1.1 | Create Project Scope & Objectives | 5 days | 2024-06-03 | 2024-06-07 |  | 1.2, 1.3, 1.4 | Tyler- PM
1.2 | Identify Key Stakeholders | 3 days | 2024-06-10 | 2024-06-13 | 1.1 | 1.3, 5.4 | Tyler- PM
1.3 | Establish Timeline & Budget | 5 days | 2024-06-14 | 2024-06-18 | 1.1, 1.2 | 1.4 | Ryan- Finance
1.4 | Develop Communication Cadence | 2 days | 2024-06-19 | 2024-06-21 | 1.1, 1.2, 1.3 | 2 | Tyler- PM
1.05
1.06
1.07
1.08
1.09
1.10
1.11
1.12
1.13
1.14
1.15
2 | Facility Blueprints (Design) |  | 2024-06-24 | 2024-08-02
2.1 | Create Site Layout | 15 days | 2024-06-24 | 2024-07-09 | 1 | 2.2, 2.3, 2.4 | Doug- Engeering
2.2 | Confirm Square Footage | 2 days | 2024-07-10 | 2024-07-12 | 2.1 | 2.3, 2.4 | Doug- Engeering
2.3 | Draft Blueprint | 5 days | 2024-07-15 | 2024-07-19 | 2.1, 2.2 | 2.4 | Doug- Engeering | [8 empty] | Task # Task / Deliverable Duration (m-days) Start Finish Predecessor Successor Resource 1.0 Project Management 6/3/2024 6/21/2024 1.1 Create Project Scope & Objectives 5 days 6/3/2024 6/7/2024 1.2, 1.3, 1.4 Tyler- PM 1.2 Identify Key Stakeholders 3 days 6/10/2024 6/13/2024 1.1 1.3, 5.4 Tyler- PM 1.3 Establish Timeline & Budget 5 days 6/14/2024 6/18/2024 1.1, 1.2 1.4 Ryan- Finance 1.4 Develop Communication Cadence 2 days 6/19/2024 6/21/2024 1.1, 1.2, 1.3 2.0 Tyler- PM 1.05 1.06 1.07 1.08 1.09 1.10 1.11 1.12 1.13 1.14 1.15 2.0 Facility Blueprints (Design) 6/24/2024 8/2/2024 2.1 Create Site Layout 15 days 6/24/2024 7/9/2024 1.0 2.2, 2.3, 2.4 Doug- Engeering 2.2 Confirm Square Footage 2 days 7/10/2024 7/12/2024 2.1 2.3, 2.4 Doug- Engeering 2.3 Draft Blueprint 5 days 7/15/2024 7/19/2024 2.1, 2.2 2.4 Doug- Engeering 2.4 Obtain LEED Approval 10 days 7/22/2024 8/2/2024 2.3 3.0 Mary- CM 2.05 2.06 2.07 2.08 2.09 2.10 2.11 2.12 2.13 2.14 2.15 3.0 Site Selection Criteria 8/5/2024 8/23/2024 3.1 Quantify Desired Proximity to Raw Materials 5 days 8/5/2024 8/9/2024 1.0, 2.0 4.0 Camille- SC 3.2 Quantify Desired Proximity to Renewable Energy Sources 5 days 8/5/2024 8/9/2024 1.0, 2.0 4.0 Doug- Engineering 3.3 Document Skilled Workforce Criteria 5 days 8/5/2024 8/9/2024 1.0, 2.0 4.0 Tonya- HR 3.4 Create Infrastructure and Logistics Criteria 10 days 8/5/2024 8/16/2024 1.0, 2.0 4.0 Doug- Engineering 3.5 Outline Regulatory Environment 10 days 8/5/2024 8/16/2024 1.0, 2.0 3.6, 4.0, 5.3 Mary- CM 3.6 List Environmental Impact and Sustainability 5 days 8/19/2024 8/23/2024 1.0, 2.0, 3.5 4.0 Mary- CM 3.07 3.08 3.09 3.1 3.11 3.12 3.13 3.14 3.15 4.0 Location Selection 8/26/2024 10/11/2024 4.1 Formulate Site Selection Report 10 days 8/26/2024 9/6/2024 1.0, 2.0, 3.0 4.2 Tyler- PM 4.2 Create Cost-Benefit Analysis 15 days 9/9/2024 9/27/2024 4.1 4.3 Ryan- Finance 4.3 Develop Risk Assessment report 10 days 9/30/2024 10/11/2024 4.2 5.0 Tyler- PM 5.0 Stakeholder Engagement 6/14/2024 11/6/2024 5.1 Attend Local Townhall Meetings 15 days 10/14/2024 11/2/2024 1.0, 2.0, 3.0, 4.0 6.0 Mary- CM 5.2 Identify Neighboring University & Trade School Partnership 3 days 11/4/2024 11/6/2024 5.1 5.1, 6.0 Tonya- HR 5.3 Secure USDA & EPA Partnership 10 days 8/19/2024 8/30/2024 3.5 6.0 Mary- CM 5.4 Establish Review Cadence with Engineering and Supply Chain 1 day 6/14/2024 6/17/2024 1.2 6.0 Tyler- PM #REF! 6.0 Permit Approval 11/7/2024 3/7/2025 6.1 Identify and Secure Federal Permits 30 days 11/7/2024 12/19/2024 3.5, 5.2 6.2 Mary- CM 6.2 Identify and Secure State Permints 25 days 1/6/2025 1/31/2025 6.1 6.3, 6.4 Mary- CM 6.3 Identify and Secure County Permits 20 days 2/3/2025 2/28/2025 5.1, 6.2 6.4 Mary- CM 6.4 Identify Recurring Permit Requirements 5 days 3/3/2025 3/7/2025 6.1, 6.2, 6.3 7.0 Mary- CM 7.0 Financial Analysis 3/10/2025 5/2/2025 7.1 Estimate construction costs & operating expenses 20 days 3/10/2025 4/4/2025 4.0, 5.0, 6.0 7.1 Ryan- Finance 7.2 Document Tax Benefits for Each Location 10 days 4/7/2025 4/18/2025 7.1 7.3 Ryan- Finance 7.3 Develop Financial Model 10 days 4/21/2025 5/2/2025 7.2 8.1 Ryan- Finance 8.0 Project Closure 5/5/2025 5/16/2025 8.1 Document lessons learned 3 days 5/5/2025 5/7/2025 7.0 8.2, 8.3 Tyler- PM 8.2 Finalize project deliverables and reports 5 days 5/8/2025 5/15/2025 8.1 8.3 Tyler- PM 8.3 Submit FInal Deliverables 1 day 5/16/2025 5/16/2025 8.2 Tyler- PM
2.4 | Obtain LEED Approval | 10 days | 2024-07-22 | 2024-08-02 | 2.3 | 3 | Mary- CM
2.05
2.06
2.07
2.08
2.09
2.10
2.11
2.12
2.13
2.14
2.15
3.0 | Site Selection Criteria |  | 2024-08-05 | 2024-08-23
3.1 | Quantify Desired Proximity to Raw Materials | 5 days | 2024-08-05 | 2024-08-09 | 1.0, 2.0 | 4 | Camille- SC
3.2 | Quantify Desired Proximity to Renewable Energy Sources | 5 days | 2024-08-05 | 2024-08-09 | 1.0, 2.0 | 4 | Doug- Engineering
3.3 | Document Skilled Workforce Criteria | 5 days | 2024-08-05 | 2024-08-09 | 1.0, 2.0 | 4 | Tonya- HR
3.4 | Create Infrastructure and Logistics Criteria | 10 days | 2024-08-05 | 2024-08-16 | 1.0, 2.0 | 4 | Doug- Engineering
3.5 | Outline Regulatory Environment | 10 days | 2024-08-05 | 2024-08-16 | 1.0, 2.0 | 3.6, 4.0, 5.3 | Mary- CM
3.6 | List Environmental Impact and Sustainability | 5 days | 2024-08-19 | 2024-08-23 | 1.0, 2.0, 3.5 | 4 | Mary- CM
3.07
3.08
3.09
3.1
3.11
3.12
3.13
3.14
3.15
4 | Location Selection |  | 2024-08-26 | 2024-10-11
4.1 | Formulate Site Selection Report | 10 days | 2024-08-26 | 2024-09-06 | 1.0, 2.0, 3.0 | 4.2 | Tyler- PM
4.2 | Create Cost-Benefit Analysis | 15 days | 2024-09-09 | 2024-09-27 | 4.1 | 4.3 | Ryan- Finance
4.3 | Develop Risk Assessment report | 10 days | 2024-09-30 | 2024-10-11 | 4.2 | 5 | Tyler- PM
5 | Stakeholder Engagement |  | 2024-06-14 | 2024-11-06
5.1 | Attend Local Townhall Meetings | 15 days | 2024-10-14 | 2024-11-02 | 1.0, 2.0, 3.0, 4.0 | 6 | Mary- CM
5.2 | Identify Neighboring University & Trade School Partnership | 3 days | 2024-11-04 | 2024-11-06 | 5.1 | 5.1, 6.0 | Tonya- HR
5.3 | Secure USDA & EPA Partnership | 10 days | 2024-08-19 | 2024-08-30 | 3.5 | 6 | Mary- CM
5.4 | Establish Review Cadence with Engineering and Supply Chain | 1 day | 2024-06-14 | 2024-06-17 | 1.2 | 6 | Tyler- PM
#REF!
6 | Permit Approval |  | 2024-11-07 | 2025-03-07
6.1 | Identify and Secure Federal Permits | 30 days | 2024-11-07 | 2024-12-19 | 3.5, 5.2 | 6.2 | Mary- CM
6.2 | Identify and Secure State Permints | 25 days | 2025-01-06 | 2025-01-31 | 6.1 | 6.3, 6.4 | Mary- CM
6.3 | Identify and Secure County Permits | 20 days | 2025-02-03 | 2025-02-28 | 5.1, 6.2 | 6.4 | Mary- CM
6.4 | Identify Recurring Permit Requirements | 5 days | 2025-03-03 | 2025-03-07 | 6.1, 6.2, 6.3 | 7 | Mary- CM
7 | Financial Analysis |  | 2025-03-10 | 2025-05-02
7.1 | Estimate construction costs & operating expenses | 20 days | 2025-03-10 | 2025-04-04 | 4.0, 5.0, 6.0 | 7.1 | Ryan- Finance
7.2 | Document Tax Benefits for Each Location | 10 days | 2025-04-07 | 2025-04-18 | 7.1 | 7.3 | Ryan- Finance
7.3 | Develop Financial Model | 10 days | 2025-04-21 | 2025-05-02 | 7.2 | 8.1 | Ryan- Finance
8 | Project Closure |  | 2025-05-05 | 2025-05-16
8.1 | Document lessons learned | 3 days | 2025-05-05 | 2025-05-07 | 7 | 8.2, 8.3 | Tyler- PM
8.2 | Finalize project deliverables and reports | 5 days | 2025-05-08 | 2025-05-15 | 8.1 | 8.3 | Tyler- PM
8.3 | Submit FInal Deliverables | 1 day | 2025-05-16 | 2025-05-16 | 8.2 |  | Tyler- PM
Task 04
Task 05
Task 06
#9 Priority deliver.
Task 01
Task 02
Task 03
Task 04
Task 06
Task 07
Task 08
Task 10
Task 11
Task 01
#10 Priority deliver.
Task 01
Task 02
Task 03
Task 04
Task 05
Task 06
Task 07
Task 08
Task 09
Task 10
Task 11
Task 12
Task 13
Task 14
#12 Priority deliver.
Task 01
Task 02
Task 03
Task 04
Task 05
Task 06
Task 07
Task 08
#13 Priority deliver.
Task 01
Task 02
Task 03
Task 04
Task 05
Task 06
Task 07
Task 08
Task 09
#14 Priority deliver.
Task 01
Task 02
Task 03
Task 04
Task 05
Task 06
Task 07
Task 08
Task 09
Task 10
#15 Priority deliver.
Task 01
Task 02
Task 03
Task 04
Task 05
Task 06
Task 07
Task 08
Task 09
Task 10
Task 11
Task 12
#16 Priority deliver.
Task 01
Task 02
Task 03
Task 04
Task 05
Task 06
Task 07
Task 08
Task 09
Task 10
Task 11
Task 12
Task 13
Task 14
#17 Priority deliver.
Task 01
Task 02
Task 03
Task 04
#18 Priority deliver.
Task 01
Task 02
Task 03
Task 04
Task 05
Task 06
Task 07
Task 08
Task 09
Task 10
Task 11
Task 12
Task 13
Task 14
Task 15
#19 Priority deliver.
Task 01
Task 02
Task 03
Task 04
#REF!
Task 06
Task 07
Task 08
#20 Priority deliver.
Task 01
Task 02
Task 04
Task 03
Formulas:
Start = [Start, row below]

## Resource Loading Table
Resource name | Work | May | June | July | August | September | October | November | December | January | Feb | March | April | May
Engineering - Doug | 136 | 4 | 7 | 17 | 25 | 21 | 10 | 18 | 11 | 5 | 5 | 5 | 4 | 4
Create Project Scope & Objectives | 5 | 2 | 3
Identify Key Stakeholders | 4 | 2 | 2
Develop Communication Cadence | 15 |  |  | 15
Create Site Layout | 3 |  |  |  | 3
Confirm Square Footage | 3 |  |  |  | 3
Draft Blueprint | 15 |  |  |  | 7 | 8
Obtain LEED Approval | 5 |  |  |  | 2 | 3
Quantify Desired Proximity to Renewable Energy Sources | 10 |  |  |  |  | 10
Document Skilled Workforce Criteria | 5 | [5 empty] | 5
Create Infrastructure and Logistics Criteria | 10 | [5 empty] | 5 | 5
List Environmental Impact and Sustainability | 7 | [6 empty] | 7
Formulate Site Selection Report | 2 | [6 empty] | 1 | 1
Create Cost-Benefit Analysis | 10 | [6 empty] | 5 | 5
Develop Risk Assessment report | 10 | [7 empty] | 5 | 5
Identify Neighboring University & Trade School Partnership | 4 |  | 2 | 2
Establish Review Cadence with Engineering and Supply Chain | 10 |  |  |  | 10
Estimate construction costs & operating expenses | 10 | [9 empty] | 5 | 5
Develop Financial Model | 2 | [11 empty] | 2
Document lessons learned | 3 | [11 empty] | 1 | 2
Finalize project deliverables and reports | 3 | [11 empty] | 1 | 2
Operations director - Sven | 87 | 11 | 14 | 15 | 0 | 0 | 7 | 11 | 6 | 3 | 5 | 7 | 4 | 4
Create Project Scope & Objectives | 6 | 3 | 3
Identify Key Stakeholders | 6 | 3 | 3
Establish Timeline & Budget | 5 | 2 | 3
Develop Communication Cadence | 3 |  |  | 3
Create Site Layout | 10 |  |  | 10
Document Skilled Workforce Criteria | 5 | [5 empty] | 5
Create Infrastructure and Logistics Criteria | 5 | [5 empty] | 2 | 3
List Environmental Impact and Sustainability | 5 | [6 empty] | 5
Formulate Site Selection Report | 2 | [6 empty] | 1 | 1
Create Cost-Benefit Analysis | 5 | [6 empty] | 2 | 3
Develop Risk Assessment report | 5 | [7 empty] | 2 | 3
Attend Local Townhall Meetings | 6 | 3 | 3
Identify Neighboring University & Trade School Partnership | 4 |  | 2 | 2
Estimate construction costs & operating expenses | 10 | [9 empty] | 5 | 5
Document Tax Benefits for Each Location | 2 | [10 empty] | 2
Develop Financial Model | 2 | [11 empty] | 2
Document lessons learned | 3 | [11 empty] | 1 | 2
Finalize project deliverables and reports | 3 | [11 empty] | 1 | 2
Finance - Ryan | 91 | 6 | 7 | 4 | 0 | 0 | 12 | 14 | 14 | 3 | 7 | 13 | 7 | 4
Establish Timeline & Budget | 12 | 6 | 6
Develop Communication Cadence | 2 |  |  | 2
Document Skilled Workforce Criteria | 10 | [5 empty] | 10
Create Infrastructure and Logistics Criteria | 5 | [5 empty] | 2 | 3
Formulate Site Selection Report | 3 | [6 empty] | 1 | 2
Create Cost-Benefit Analysis | 20 | [6 empty] | 10 | 10
Develop Risk Assessment report | 5 | [7 empty] | 2 | 3
Identify Neighboring University & Trade School Partnership | 3 |  | 1 | 2
Estimate construction costs & operating expenses | 15 | [9 empty] | 7 | 8
Document Tax Benefits for Each Location | 5 | [10 empty] | 5
Develop Financial Model | 5 | [11 empty] | 5
Document lessons learned | 3 | [11 empty] | 1 | 2
Finalize project deliverables and reports | 3 | [11 empty] | 1 | 2
HR - Tonya | 49 | 0 | 10 | 10 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 2 | 4 | 3
Document Skilled Workforce Criteria | 20 | [5 empty] | 20
Identify Neighboring University & Trade School Partnership | 20 |  | 10 | 10
Document Tax Benefits for Each Location | 2 | [10 empty] | 2
Develop Financial Model | 2 | [11 empty] | 2
Document lessons learned | 3 | [11 empty] | 1 | 2
Finalize project deliverables and reports | 2 | [11 empty] | 1 | 1
Supply Chain - Camille | 83 | 6 | 7 | 10 | 5 | 10 | 7 | 14 | 8 | 3 | 2 | 3 | 4 | 4
Create Project Scope & Objectives | 6 | 3 | 3
Identify Key Stakeholders | 6 | 3 | 3
Develop Communication Cadence | 3 |  |  | 3
Create Site Layout | 5 |  |  | 5
Quantify Desired Proximity to Raw Materials | 10 |  |  |  |  | 10
Document Skilled Workforce Criteria | 5 | [5 empty] | 5
Create Infrastructure and Logistics Criteria | 5 | [5 empty] | 2 | 3
List Environmental Impact and Sustainability | 7 | [6 empty] | 7
Formulate Site Selection Report | 5 | [6 empty] | 2 | 3
Create Cost-Benefit Analysis | 5 | [6 empty] | 2 | 3
Develop Risk Assessment report | 5 | [7 empty] | 2 | 3
Identify Neighboring University & Trade School Partnership | 3 |  | 1 | 2
Establish Review Cadence with Engineering and Supply Chain | 5 |  |  |  | 5
Estimate construction costs & operating expenses | 5 | [9 empty] | 2 | 3
Develop Financial Model | 2 | [11 empty] | 2
Document lessons learned | 3 | [11 empty] | 1 | 2
Finalize project deliverables and reports | 3 | [11 empty] | 1 | 2
Automative GM - Russel | 67 | 8 | 11 | 5 | 2 | 12 | 0 | 0 | 0 | 6 | 7 | 5 | 6 | 5
Create Project Scope & Objectives | 6 | 3 | 3
Establish Timeline & Budget | 5 | 2 | 3
Confirm Square Footage | 1 |  |  |  | 1
Draft Blueprint | 3 |  |  |  | 1 | 2
Quantify Desired Proximity to Raw Materials | 5 |  |  |  |  | 5
Quantify Desired Proximity to Renewable Energy Sources | 5 |  |  |  |  | 5
Attend Local Townhall Meetings | 6 | 3 | 3
Identify Neighboring University & Trade School Partnership | 5 |  | 2 | 3
Secure USDA & EPA Partnership | 2 |  |  | 2
Identify and Secure Federal Permits | 3 | [8 empty] | 3
Identify and Secure State Permints | 3 | [8 empty] | 3
Identify and Secure County Permits | 3 | [9 empty] | 3
Identify Recurring Permit Requirements | 3 | [9 empty] | 3
Estimate construction costs & operating expenses | 3 | [9 empty] | 1 | 2
Document Tax Benefits for Each Location | 3 | [10 empty] | 3
Develop Financial Model | 2 | [11 empty] | 2
Document lessons learned | 4 | [11 empty] | 2 | 2
Finalize project deliverables and reports | 5 | [11 empty] | 2 | 3
Complaince Manager - Mary | 123 | 6 | 9 | 18 | 7 | 11 | 0 | 25 | 10 | 15 | 11 | 5 | 2 | 4
Create Project Scope & Objectives | 5 | 2 | 3
Identify Key Stakeholders | 5 | 2 | 3
Develop Communication Cadence | 3 |  |  | 3
Create Site Layout | 3 |  |  | 3
Confirm Square Footage | 1 |  |  |  | 1
Draft Blueprint | 2 |  |  |  | 1 | 1
Obtain LEED Approval | 10 |  |  |  | 5 | 5
Quantify Desired Proximity to Renewable Energy Sources | 5 |  |  |  |  | 5
Outline Regulatory Environment | 10 | [6 empty] | 10
List Environmental Impact and Sustainability | 10 | [6 empty] | 10
Formulate Site Selection Report | 10 | [6 empty] | 5 | 5
Develop Risk Assessment report | 10 | [7 empty] | 5 | 5
Attend Local Townhall Meetings | 5 | 2 | 3
Secure USDA & EPA Partnership | 12 |  |  | 12
Identify and Secure Federal Permits | 5 | [8 empty] | 5
Identify and Secure State Permints | 5 | [8 empty] | 5
Identify and Secure County Permits | 5 | [9 empty] | 5
Identify Recurring Permit Requirements | 5 | [9 empty] | 5
Estimate construction costs & operating expenses | 3 | [9 empty] | 1 | 2
Document Tax Benefits for Each Location | 3 | [10 empty] | 3
Document lessons learned | 3 | [11 empty] | 1 | 2
Finalize project deliverables and reports | 3 | [11 empty] | 1 | 2
Project Manager - Tyler | 221 | 24 | 29 | 16 | 17 | 14 | 0 | 27 | 23 | 18 | 10 | 6 | 18 | 19
Create Project Scope & Objectives | 16 | 8 | 8
Identify Key Stakeholders | 10 | 5 | 5
Establish Timeline & Budget | 6 | 3 | 3
Develop Communication Cadence | 5 |  |  | 5
Create Site Layout | 3 |  |  | 3
Confirm Square Footage | 1 |  |  |  | 1
Draft Blueprint | 3 |  |  |  | 1 | 2
Obtain LEED Approval | 3 |  |  |  | 1 | 2
Quantify Desired Proximity to Raw Materials | 5 |  |  |  |  | 5
Quantify Desired Proximity to Renewable Energy Sources | 5 |  |  |  |  | 5
Outline Regulatory Environment | 5 | [6 empty] | 5
List Environmental Impact and Sustainability | 10 | [6 empty] | 10
Formulate Site Selection Report | 15 | [6 empty] | 7 | 8
Create Cost-Benefit Analysis | 10 | [6 empty] | 5 | 5
Develop Risk Assessment report | 20 | [7 empty] | 10 | 10
Attend Local Townhall Meetings | 16 | 8 | 8
Identify Neighboring University & Trade School Partnership | 10 |  | 5 | 5
Secure USDA & EPA Partnership | 3 |  |  | 3
Establish Review Cadence with Engineering and Supply Chain | 14 |  |  |  | 14
Identify and Secure Federal Permits | 4 | [8 empty] | 4
Identify and Secure State Permints | 4 | [8 empty] | 4
Identify and Secure County Permits | 4 | [9 empty] | 4
Identify Recurring Permit Requirements | 4 | [9 empty] | 4
Estimate construction costs & operating expenses | 5 | [9 empty] | 2 | 3
Document Tax Benefits for Each Location | 3 | [10 empty] | 3
Develop Financial Model | 2 | [11 empty] | 2
Document lessons learned | 16 | [11 empty] | 8 | 8
Finalize project deliverables and reports | 16 | [11 empty] | 8 | 8
Submit Final Deliverables | 3 | [12 empty] | 3

## Time Phased Budget
Activities | Total Value | May | June | July | August | September | October | November | December | January | Feb | March | April | May
Project Management
Create Project Scope & Objectives | 2215 | 1107.5 | 1107.5
Identify Key Stakeholders | 1480 | 740 | 740
Establish Timeline & Budget | 1535 | 767.5 | 767.5
Develop Communication Cadence | 1048 |  |  | 1048
6278
Facility Blueprints (Design)
Create Site Layout | 1188 |  |  | 1188
Confirm Square Footage | 296 |  |  |  | 296
Draft Blueprint | 1112 |  |  |  | 556 | 556
Obtain LEED Approval | 835 |  |  |  | $417.5+$1000 | 417.5+$1000
5431
Site Selection Criteria
Quantify Desired Proximity to Raw Materials | 1025 |  |  |  |  | $1025 +$10,000
Quantify Desired Proximity to Renewable Energy Sources | 805 |  |  |  |  | $805+$10,000
Document Skilled Workforce Criteria | 2190 | [5 empty] | 2190
Create Infrastructure and Logistics Criteria | 1200 | [5 empty] | 600 | 600
Outline Regulatory Environment | 710 | [6 empty] | 710
List Environmental Impact and Sustainability | 1840 | [6 empty] | 1840
25930
Location Selection
Formulate Site Selection Report | 1925 | [6 empty] | 962.5 | 962.5
Create Cost-Benefit Analysis | 2525 | [6 empty] | 1262.5 | 1262.5
Develop Risk Assessment report | 2660 | [7 empty] | $1330+$2500 | $1330+$2500
12110
Stakeholder Engagement
Attend Local Townhall Meetings | 1720 | $860+$750 | $860+$750
Identify Neighboring University & Trade School Partnership | 2445 |  | $1222.5+$750 | $1222.5+$750
Secure USDA & EPA Partnership | 832 |  |  | 832
Establish Review Cadence with Engineering and Supply Chain | 1375 |  |  |  | 1375
9372
Permit Approval
Identify and Secure Federal Permits | 625 | [8 empty] | $625+$4000
Identify and Secure State Permints | 625 | [8 empty] | $625+$2000
Identify and Secure County Permits | 625 | [9 empty] | $625+$1500
Identify Recurring Permit Requirements | 625 | [9 empty] | 625
10000
Financial Analysis
Estimate construction costs & operating expenses | 2583 | [9 empty] | 1291.5 | 1291.5
Document Tax Benefits for Each Location | 952 | [10 empty] | 952
Develop Financial Model | 879 | [11 empty] | 879
4414
Project Closure
Document lessons learned | 1924 | [11 empty] | 962 | 962
Finalize project deliverables and reports | 1942 | [11 empty] | 971 | 971
Submit Final Deliverables | 150 | [12 empty] | 150
4016
Risk Mitigation / Buffer | 64000 | [13 empty] | 64000
Total Value per Day |  | 4225 | 6197.5 | 5040.5 | 3644.5 | 23803.5 | 2790 | 5375 | 6055 | 11080 | 4041.5 | 2243.5 | 2812 | 2083 | 64000
Cummulative Value |  | 4225 | 10422.5 | 15463 | 19107.5 | 42911 | 45701 | 51076 | 57131 | 68211 | 72252.5 | 74496 | 77308 | 79391 | 143391

## ProbSol (hidden)
Paste correct-sized arrow or dashes in the narrow column and the wording in the wider column for each constraint for each alternative
Problem Solving Tool
Project Details Problem #:
|  | Date: |  |  |  | Project #:
Project Manager:
Project Name:
Problem Statement:
Alternatives
Scaled Arrows for size of impact |  |  |  | Problem/Do nothing | 1 |  | 2 |  | 3 | 4 | 5
↑ | ↑ | C | ↓ |  | ↑ | 60K INCREASE | ↑ | 40k increase | ↑
← | ← | S | -- |  | ← |  | → |  | → | --
→ | → | P | ↓ |  | ↓ |  | -- |  | -- | --
↓ | ↓ | RISK | ↓ |  | ↓ |  | -- |  | --
↑ | ↑
← | ←
→ | → | ALTERNATIVE 1:
↓ | ↓
↑ | ↑ | ALTERNATIVE 2:
← | ← | [10 empty] | →
→ | → | ALTERNATIVE 3:
↓ | ↓
↑ | ↑ | ALTERNATIVE 4:
← | ←
→ | → | ALTERNATIVE 5:
↓ | ↓
RECOMMENDATION:

## P-Increm (hidden)
= Deliverable
= Enabler
= Risk / Critical
| Week 1+2 | Week 3+4 | Week 5-6 | Week 7-8 | Week 9-10 | Week 11-12 |  | Week 13+14 | Week 15+16 | Week 17+18 | Week 19+20 | Week 21+22 | Week 23-24
| Iteration 1 | Iteration 2 | Iteration 3 | Iteration 4 | Iteration 5 | Iteration 6 |  | Iteration 7 | Iteration 8 | Iteration 9 | Iteration 10 | Iteration 1 | Iteration 12
LOAD: | [6 empty] | LOAD:
AVAILABILITY: | [6 empty] | AVAILABILITY:
Roadmap Milestones | [6 empty] | Roadmap Milestones
Set PI Objectives (1) | [6 empty] | Set PI Objectives (2)
Scrum Team 1 | [6 empty] | Scrum Team 1
Scrum Team 2 | [6 empty] | Scrum Team 2
Scrum Team 3 | [6 empty] | Scrum Team 3
Business team | [6 empty] | Business team
Services team | [6 empty] | Services team
Supplier team | [6 empty] | Supplier team

## Kanban (hidden)
| Iteration x.x |  | LOAD
KANBAN BOARD | from date to date |  | AVAILABILITY
Deliverables | TO DO | DOING | DONE | Our Done criteria: